## Risk log
Risk Log: Buckinghamshire Local Enterprise Partnership | [5 empty] | Date of last update: 29.1.19 By: RH/IB
Risk Detail | [5 empty] | Risk Assessment |  |  |  | Mitigation
Ref. | Date | Review | Raised by | Owner | Description | Likelihood | Impact | Overall Severity | Change Since Feb 20 | Mitigating Action or Controls | Closed
1 | 2020-01-29 | 28.4.20 | Board | RH/AS | Dissolution of LEPs due to weakening relationship with Government and certainty of capital and revenue funding. | 2 | 4 | 8 | Decrease (Feb likelihood 3) | Maintain close relatinships with MP's & LEP Network. Ensure delivery against Government targets through Annual Performance Review. Ensure that reserve balances are sufficient to maintian delivery independently | No
2 | 2020-01-29 | 28.4.20 | Board | RH/IB | Potential for Bucks LEP to be marginalised due to weakening LEP role and relationship with partners within Oxford Cambridge Arc. particularly the ARC LEPs and the Buckinghamshire Growth Board. Positioning of Bucks Industrial Strategy within wider national growth context. | 3 | 3 | 9 | Increase (Feb likelihood 2) | Ensure Bucks LEP are integral I developing Arc wide proposiitons, maintain open and positive relationship with Arc neighbours. Maintain close working relationship with Arc Universities Group. Increase risk of Arc activity not being prioritised due to national Civid 19 Emergency Activity. | No
3 | 2020-01-29 | 28.4.20 | Board | RH | Failure to implement Local Industrial Strategy due to prioritisation, structure and or insufficient resource. | 3 | 4 | 12 | Increase (Feb likelihood 2) | Advisory panel and delivery sub-board structure implemented, board approval to support team delivery resilience. Increased risk due to short term focus on COVID 19 Emergency Activities. Need to reposition LIS delivery as part of Recovery Programme. | No
4 | 2020-01-29 | 28.4.20 | Board | RH/AS/MT | Duplication of economic activity with Buckinghamshire Council. | 1 | 4 | 4 | No Change | Ensure close working relationship with senior executive officers and members of the new authority. Ensure all members are aware of the impact of LEP supported services. Good working relationship established as part of Recovery Programme. | No
5 | 2020-01-29 | 28.4.20 | Board | RemNom Committee | Failure to comply with natioinal guidelines on board diversity. Board member recruitment. Characteristics, capacity, diversity and capability on the Board to be in line with the LEP Review. | 2 | 3 | 6 | No change | Terms of reference of RemNom committee to ensure board membership reflects appropriate diversity and skills needs for Buckinghamshire. HR suport now provided by independent agency. | No
6 | 2020-01-29 | 28.4.20 | Board | RH/PB | Failure to complete of MOU and complete successful implementation of agreement with BBF over finance, HR and data security. Capacity of LEP to deliver on its obligations while maintaining operationally robust and secure systems and procedures. | 2 | 3 | 6 | No Change | Weekly operational meetings arranged between LEP & BBF Executive Teams - extended to daily meetings in remote working operation . | No
7 | 2020-01-29 | 28.4.20 | Board | JR | Reputational damage to BLEP as a result of strategic/delivery partner failure/position. | 4 | 3 | 12 | Increase (Feb likelihood 3) | Quarterly meetings with all project sponsors, contract agreement ensures partners notify LEP of any major change to LGF programme delivery schedule. Risk increased due to Covid 19 Business Conditions. | No
8 | 2020-01-29 | 28.4.20 | Board | JR | Failure to achieve full and total spend on LGF programme by March 2021. | 3 | 4 | 12 | No Change | Quarterly meetings with all project sponsors, contract agreement ensures partners notify LEP of any major change to LGF programme delivery schedule. | No
9 | 2020-01-29 | 28.4.20 | Board | RH | Failure to secure funding to run ancillary programmes such as growth hub, skills team, Enterprise Zone and BA | 3 | 4 | 12 | No Change | Ensure all Government programme support submissions are met and ensure that reserves allow for core services to be delivered for 3 months following any loss of funding. | No
10 | 2020-01-29 | 28.4.20 | Board | RH/AS | Failure to Secure Aylesbury Woodlands planning promotion and Eastern Link Road delivery. | 4 | 4 | 16 | No Change | Continued Executive Participation in Woodlands Stakeholder Board. | No
11 | [5 empty] | 0 | 0 | 97 | Feb Total 91 (Up6)
12 | [5 empty] | 0 | 0 | 0
13 | [5 empty] | 0 | 0 | 0
14 | [5 empty] | 0 | 0 | 0
15 | [5 empty] | 0 | 0 | 0

## Issue log
Issue Log: Buckinghamshire Local Enterprise Partnership (order by overall severity) | [5 empty] | Date of last update: XXX By: XXX
Issue Detail | [5 empty] | Issue Assessment |  |  |  | Mitigation
Ref. | Date | Review | Raised by | Owner | Description | Likelihood | Impact | Overall Severity | Change Since Feb 20 | Mitigating Action or Controls | Closed
1 |  | 28.4.20 |  |  | Dissolution of LEPs due to weakening relationship with Government and certainty of capital and revenue funding. | 2 | 0 | 0 | Decrease (Feb likelihood 3)
2 |  | 28.4.20 |  |  | Potential for Bucks LEP to be marginalised due to weakening LEP role and relationship with partners within Oxford Cambridge Arc. particularly the ARC LEPs and the Buckinghamshire Growth Board. Positioning of Bucks Industrial Strategy within wider national growth context. | 3 | 0 | 0 | Increase (Feb likelihood 2) | Ensure Bucks LEP are integral I developing Arc wide proposiitons, maintain open and positive relationship with Arc neighbours. Maintain close working relationship with Arc Universities Group. Increase risk of Arc activity not being prioritised due to national Civid 19 Emergency Activity.
3 |  | 28.4.20 |  |  |  | 3 | 0 | 0 | Increase (Feb likelihood 2) | Advisory panel and delivery sub-board structure implemented, board approval to support team delivery resilience. Increased risk due to short term focus on COVID 19 Emergency Activities. Need to reposition LIS delivery as part of Recovery Programme.
4 |  | 28.4.20 |  |  | Duplication of economic activity with Buckinghamshire Council. | 0 | 0 | 0 | No Change | Ensure close working relationship with senior executive officers and members of the new authority. Ensure all members are aware of the impact of LEP supported services. Good working relationship established as part of Recovery Programme.
5 |  | 28.4.20 |  |  | Failure to comply with natioinal guidelines on board diversity. Board member recruitment. Characteristics, capacity, diversity and capability on the Board to be in line with the LEP Review. | 0 | 0 | 0 | No change | Terms of reference of RemNom committee to ensure board membership reflects appropriate diversity and skills needs for Buckinghamshire. HR suport now provided by independent agency.
6 |  | 28.4.20 |  |  | Failure to complete of MOU and complete successful implementation of agreement with BBF over finance, HR and data security. Capacity of LEP to deliver on its obligations while maintaining operationally robust and secure systems and procedures. | 0 | 0 | 0 | No Change | Weekly operational meetings arranged between LEP & BBF Executive Teams - extended to daily meetings in remote working operation .
7 |  | 28.4.20 |  |  |  | 4 | 0 | 0 | Increase (Feb likelihood 3) | Quarterly meetings with all project sponsors, contract agreement ensures partners notify LEP of any major change to LGF programme delivery schedule. Risk increased due to Covid 19 Business Conditions.
8 |  | 28.4.20 |  |  |  | 0 | 0 | 0 | No Change
9 |  | 28.4.20 |  |  |  | 0 | 0 | 0 | No Change
10 |  | 28.4.20 |  |  |  | 0 | 0 | 0 | No Change
11 | [5 empty] | 0 | 0 | 0 | Feb Total 91 (Up6)
12 | [5 empty] | 0 | 0 | 0
13 | [5 empty] | 0 | 0 | 0
14 | [5 empty] | 0 | 0 | 0
15 | [5 empty] | 0 | 0 | 0

## Scoring matrix
Impact
|  |  | Very low | Low | Medium | High | Severe | Change Since Feb 20
| 28.4.20 |  | 1 | Dissolution of LEPs due to weakening relationship with Government and certainty of capital and revenue funding. | 2 | 4 | 5 | Decrease (Feb likelihood 3)
Likelihood | 28.4.20 | 1 | 1 | Potential for Bucks LEP to be marginalised due to weakening LEP role and relationship with partners within Oxford Cambridge Arc. particularly the ARC LEPs and the Buckinghamshire Growth Board. Positioning of Bucks Industrial Strategy within wider national growth context. | 3 | 4 | 5 | Increase (Feb likelihood 2) | Ensure Bucks LEP are integral I developing Arc wide proposiitons, maintain open and positive relationship with Arc neighbours. Maintain close working relationship with Arc Universities Group. Increase risk of Arc activity not being prioritised due to national Civid 19 Emergency Activity.
[8 empty] | Increase (Feb likelihood 2) | Advisory panel and delivery sub-board structure implemented, board approval to support team delivery resilience. Increased risk due to short term focus on COVID 19 Emergency Activities. Need to reposition LIS delivery as part of Recovery Programme.
| 28.4.20 | 2 | 2 | Duplication of economic activity with Buckinghamshire Council. | 6 | 8 | 10 | No Change | Ensure close working relationship with senior executive officers and members of the new authority. Ensure all members are aware of the impact of LEP supported services. Good working relationship established as part of Recovery Programme.
[8 empty] | No change | Terms of reference of RemNom committee to ensure board membership reflects appropriate diversity and skills needs for Buckinghamshire. HR suport now provided by independent agency.
| 28.4.20 | 3 | 3 | Failure to complete of MOU and complete successful implementation of agreement with BBF over finance, HR and data security. Capacity of LEP to deliver on its obligations while maintaining operationally robust and secure systems and procedures. | 6 | 12 | 15 | No Change | Weekly operational meetings arranged between LEP & BBF Executive Teams - extended to daily meetings in remote working operation .
[8 empty] | Increase (Feb likelihood 3) | Quarterly meetings with all project sponsors, contract agreement ensures partners notify LEP of any major change to LGF programme delivery schedule. Risk increased due to Covid 19 Business Conditions.
| 28.4.20 | 4 | 4 | #VALUE! | 8 | 16 | 20 | No Change
No Change
| 28.4.20 | 5 | 5 | #VALUE! | 10 | 20 | 25 | No Change
Feb Total 91 (Up6)